## Foorbis
Start |  | 2021-08-16 | 2021-08-23 | 2021-08-30 | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 | 2021-10-04 | 2021-10-11 | 2021-10-18
End |  | 2021-08-23 | 2021-08-30 | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2021-10-25
Days since start |  | 7 | 14 | 21 | 28 | 35 | 42 | 49 | 56 | 63 | 70
Design |  | 2021-08-23: 6*2 =12 screens 1. Register - DONE 2. Login - DONE 3. Forgot password - remaining 4. Side menu - MonProfil-Utilisateur - DONE 5. Header-Utilisateur - design 6. Header-Professionnel - design issue 7. Side menu - Dashboard Pro - design issue 8. Dashboard-Pro-VueUtilisateurClient - design issue 9. MesAnnonces-Pro - multi ple categories 10. MesAnnonces-Pro-NouvelleAnnonce - DONE 11. MesAnnonces-Pro-Mettre-a-jour-Annonce - DONE 12. MesAnnonces-Pro-PaiementNouvelleAnnonce - DONE; 2021-08-30: 6*2 =12 screens 1. 2.07. MesAnnonces-Pro-NouvelleAnnonce-NePasRenouveller - design issue remaining Become pro screens - DONE 2. 2.01.Annonces_Utilisateur-Filtre - design issue 3. 2.02. Annonces_Utilisateur-MesFavoris - DONE 4. 05. Recherche - remaining 5. 06. Recherche-Filtres - remaining 6. 4.01 Header-over-Forum - on scroll load remaining 7. 4.02 Header-over-Forum-NouvelleQuestion - DONE 8. 5.01. Messagerie - delete and live remaining 9. 1.02 Dashboard-Pro-Paramêtre - design issue 10. Header-over-Recrutement-Recruteur - design 11. Header-over-Recrutement-Recruteur-CréationOffre - design issue 12. Header-over-Recrutement-VoirOffre -design issue; 2021-09-06: 6*2 1. Header-over-Recrutement-Candidat - DONE 2. Header-over-Recrutement-Postuler - DONE 3. FAdmin(FoorbisAdmin)*2 - remaining 4. FAdmin(FoorbisAdmin)*2 - remaining 5. FAdmin(FoorbisAdmin)*2 - remaining 6. Header-over-Actualités - design issue 7. Header-over-Actualités-Article - design issue 8. Header-over-Apropos-DonnerVotreAvis - share 9. Header-over-Apropos-FAQ - share 10. Header-over-Messagerie - live chat remaining 11. Header-over-notifications - remaining 12. Header-over-Paramètre - remaining
Database design |  | 2021-08-23: Complete database design for all functinoalities- Done; 2021-08-30: Database design review Project setup Roles setup
Basic Functionality |  | 2021-08-30: 1. Register -DONE 2. Login -DONE 3. Forgot password -DONE 4. Logout -DONE
Annonces Payment gateway Social integration | Dev1 | 2021-09-06: 4. Side menu - MonProfil-Utilisateur -DONE 5. Header-Utilisateur -DONE Become pro screens -DONE 6. Header-Professionnel -DONE; 2021-09-13: 7. Side menu - Dashboard Pro - multiple categories design 8. Dashboard-Pro-VueUtilisateurClient - announces design 9. MesAnnonces-Pro - design issue 10. MesAnnonces-Pro-NouvelleAnnonce - done 11. MesAnnonces-Pro-Mettre-a-jour-Annonce; 2021-09-20: 12. MesAnnonces-Pro-PaiementNouvelleAnnonce 1. 2.07. MesAnnonces-Pro-NouvelleAnnonce-NePasRenouveller 2. 2.01.Annonces_Utilisateur-Filtre 3. 2.02. Annonces_Utilisateur-MesFavoris; 2021-09-27: 8. 5.01. Messagerie - design issue and live 9. 1.02 Dashboard-Pro-Paramêtre - design issue; 2021-10-04: Integration 10. Header-over-Messagerie 11. Header-over-notifications 12. Header-over-Paramètre
Search | Dev 2 | 2021-09-06: 6. 4.01 Header-over-Forum - share 7. 4.02 Header-over-Forum-NouvelleQuestion - design issue 10. Header-over-Recrutement-Recruteur - share 11. Header-over-Recrutement-Recruteur-CréationOffre - design issue 12. Header-over-Recrutement-VoirOffre - design issue; 2021-09-13: 1. Header-over-Recrutement-Candidat - DONE 2. Header-over-Recrutement-Postuler - DONE; 2021-09-20: 4. 05. Recherche - remaining 5. 06. Recherche-Filtres - remaining; 2021-09-27: 3. FAdmin(FoorbisAdmin) 4. FAdmin(FoorbisAdmin) 5. FAdmin(FoorbisAdmin); 2021-10-04: 6. Header-over-Actualités 7. Header-over-Actualités-Article 8. Header-over-Apropos-DonnerVotreAvis 9. Header-over-Apropos-FAQ